**FIRST DRAFT — COUNSEL REVIEW PLAN**

>

This is Birthright Foundation's proposed review plan for outside

counsel. It segments every legal instrument into **Essential**

(must review and ratify before any binding use) and **Optional**

(nice-to-have polish; can be signed off later or in batch).

>

Time estimates assume a competent generalist attorney reading

the current first drafts (which are already in accepted standard

boilerplate). They are budgeting numbers, not commitments.

>

Version: February 2026 · Birthright Foundation (birthright.live)

# Counsel Review Plan — Segmented Effort & Time Budget

## Summary

| Segment | Time (min) | Hours |
| --- | --- | --- |
| Essential — Section A (public + revenue) | 635 | 10.6 |
| Essential — Section B (governance) | 320 | 5.3 |
| Essential subtotal | 955 | 15.9 |
| Optional — Section C (partner niches) | 200 | 3.3 |
| Optional — Section D (internal plans) | 170 | 2.8 |
| Optional subtotal | 370 | 6.2 |
| Grand total (all 22 instruments) | 1,325 | 22.1 |

Reading assumption: 22 documents, average ~3–4 pages each, plus one

"Nonprofit Governance Bundle" doc that is really five sub-instruments

budgeted separately. The ISTV memo is an advisory memo, not a

contract — it is included for context only.

Recommended sequencing

Ratify Section A first (10.6 hrs) — every public-facing +

revenue-adjacent document. Nothing user-hits or partner-hits

without a Section A ratification.

Ratify Section B next (5.3 hrs) — governance bundle. Needed

before board seats are filled and before D&O policy binds.

Ratify Section C in batches as those partner types onboard.

Section D is planning material — can be sanity-checked with

the compliance vendor rather than counsel.

## Section A — Essential · Public-Facing & Revenue (635 min · 10.6 hrs)

The five documents any real user or partner actually reads or signs.

Ratifying these unblocks the entire consumer-facing product.

### A1 · Terms of Service (`01-terms-of-service`)

Standard 16-section consumer terms. AI clause, arbitration jurisdiction,

sliding-scale, and print-partner data sharing are the non-standard bits.

| Subsection | Time | Rationale |
| --- | --- | --- |
| §§1–4 Acceptance / eligibility | 5 | Boilerplate |
| §5 Products / workshops / AI wallet | 15 | Confirm merchant + POD flow-through language |
| §6 Conduct | 5 | Standard |
| §7 UGC licence | 10 | Confirm sublicensable scope |
| §8 AI features | 10 | Non-standard — human-in-loop wording |
| §9 Payments | 5 | Stripe scoping |
| §§10–13 Termination / warranty / liability / indemnity | 15 | Standard limitation-of-liability, confirm $ cap |
| §14 Governing law | 5 | Confirm NC choice |
| §§15–16 Change control / contact | 5 | Standard |
| Total | 75 |  |

### A2 · Privacy Policy (`02-privacy-policy`)

CCPA + GDPR-lite. The lawful-bases + subprocessor list is where

attention is due.

| Subsection | Time |
| --- | --- |
| §§1–3 Data + purposes + bases | 20 |
| §4 Subprocessor list | 15 |
| §5 Retention schedule | 10 |
| §6 Rights + DSAR | 15 |
| §7 Security | 10 |
| §§8–10 Children / AI / changes | 10 |
| §11 Contact + DPO reference | 5 |
| Total | 85 |

### A3 · Cookie & Tracking Notice (`03-cookie-notice`)

Short. Focus on the third-party provider table and consent mechanics.

| Subsection | Time |
| --- | --- |
| Categories + controls | 10 |
| Third-party table | 10 |
| Retention | 5 |
| Total | 25 |

### A4 · Universal Indemnification / Hold-Harmless (`04-indemnification-hold-harmless`)

Signed by every workshop participant + partner. This is a real waiver — read carefully.

| Subsection | Time |
| --- | --- |
| §§1–2 Voluntary + no-advice | 10 |
| §3 Hold-harmless scope | 15 |
| §4 Indemnity by user | 10 |
| §§5–8 Data / conduct / version / law | 10 |
| Enforceability under NC law | 15 |
| Total | 60 |

### A5 · Refund & Returns Policy (`15-refund-returns-policy`)

Consumer-facing. EU withdrawal + POD-vs-stock rules are the risk points.

| Subsection | Time |
| --- | --- |
| Products (POD vs stock) | 15 |
| Workshops | 10 |
| Subscriptions | 5 |
| AI wallet + sponsorships | 5 |
| EU/UK withdrawal | 10 |
| Total | 45 |

### A6 · Facilitator Services Agreement + IP Assignment (`05-facilitator-services-agreement`)

Revenue-critical + IC classification.

| Subsection | Time |
| --- | --- |
| §1 IC relationship | 10 |
| §§2–3 Services + fees | 15 |
| §4 Standards of care | 10 |
| §5 IP (BF licence + assignment) | 25 |
| §6 Confidentiality | 5 |
| §§7–11 Term / indemnity / non-solicit / law | 25 |
| Total | 90 |

### A7 · Artist Consignment Agreement (`06-artist-consignment-agreement`)

Title + 20% Foundation gift are custom terms.

| Subsection | Time |
| --- | --- |
| §§1–3 Relationship + list + pricing | 20 |
| §§4–5 Fulfilment + returns | 10 |
| §6 IP + publicity | 15 |
| §§7–10 Payouts / term / indemnity / law | 25 |
| Total | 70 |

### A8 · Vendor Supplier / Dropship Agreement (`07-vendor-supplier-agreement`)

Product-liability + insurance clause needs local counsel eye.

| Subsection | Time |
| --- | --- |
| §§1–4 Relationship + listings + prices + fulfilment | 30 |
| §5 Warranty + returns | 15 |
| §6 IP | 10 |
| §§7–10 Payouts / indemnity / insurance / law | 30 |
| Total | 85 |

### A9 · Community Partner Referral Agreement (`08-community-partner-referral-agreement`)

Straightforward marketing standards + attribution.

| Subsection | Time |
| --- | --- |
| §§1–5 IC / referral / comp / marketing | 30 |
| §§6–9 Term / IP / indemnity / law | 20 |
| Total | 50 |

### A10 · Sponsorship Agreement / Recognition Consent (`09-sponsorship-agreement`)

Tax-status disclosure + recognition licence.

| Subsection | Time |
| --- | --- |
| Pledge + tax status (§§1–2) | 15 |
| Recognition + logo licence (§§3–4) | 15 |
| Non-endorsement + refunds (§§5–6) | 10 |
| Contingency + confidentiality (§§7–8) | 10 |
| Total | 50 |

Section A subtotal: 635 minutes (10 hours 35 minutes)

## Section B — Essential · Governance (320 min · 5.3 hrs)

Needed before the Board seats fill and before D&O binds. Also needed to

support the 501(c)(3) submission.

### B1 · Board Member / Officer Agreement + D&O (`11-board-officer-agreement`)

| Subsection | Time |
| --- | --- |
| §§1–3 Role / term / fiduciary | 15 |
| §4 Conflicts (link to policy) | 10 |
| §5 Confidentiality | 10 |
| §§6–7 Compensation / time | 5 |
| §8 Indemnification + D&O terms | 20 |
| §§9–10 Removal + law | 10 |
| Total | 70 |

### B2 · Volunteer Agreement (`12-volunteer-agreement`)

| Subsection | Time |
| --- | --- |
| Scope + IP + confidentiality | 20 |
| Safety + insurance | 10 |
| Data / law | 10 |
| Total | 40 |

### B3 · Ombudsman Charter (`13-ombudsman-charter`)

| Subsection | Time |
| --- | --- |
| IOA standards + scope | 10 |
| Confidentiality | 10 |
| Independence + records | 10 |
| Total | 30 |

### B4 · Community Standards / Content Moderation Policy (`14-community-standards`)

| Subsection | Time |
| --- | --- |
| Prohibited content | 10 |
| Handle-with-care | 5 |
| Enforcement ladder | 10 |
| Reporting + appeals | 10 |
| DSA scope check | 5 |
| Total | 40 |

### B5 · Sliding-Scale & Scholarship Terms (`10-sliding-scale-scholarship-terms`)

| Subsection | Time |
| --- | --- |
| Tier definitions | 5 |
| Scholarship + refunds | 10 |
| Total | 15 |

### B6 · Data Processing Agreement Template (`19-data-processing-agreement-template`)

GDPR Art. 28 template. Read once — reused per subprocessor.

| Subsection | Time |
| --- | --- |
| §§1–4 Scope / subprocessors / security | 20 |
| §5 Breach | 10 |
| §§6–8 DSAR / transfers / audit | 15 |
| §§9–11 Return / liability / law | 10 |
| Annexes 1 + 2 | 15 |
| Total | 70 |

### B7 · Nonprofit Governance Bundle (`20-nonprofit-governance-bundle`)

Five sub-instruments. Break them out:

| Sub-doc | Time |
| --- | --- |
| A · Articles of Incorporation | 15 |
| B · Bylaws | 20 |
| C · Conflict-of-Interest | 10 |
| D · Whistleblower | 5 |
| E · Records Retention | 5 |
| Total | 55 |

Section B subtotal: 320 minutes (5 hours 20 minutes)

## Section C — Optional · Partner Niches (200 min · 3.3 hrs)

None of these blocks a launch. Batch-review when the corresponding

partner type onboards.

### C1 · Sponsor Recognition Consent (already batched into A10 — no extra time)

### C2 · Steward Volunteer Agreement (already covered by B2 — no extra time)

### C3 · Research Collaborator Honoraria Rider — **to be drafted** — 45

Standalone honoraria payment terms + IP licence for research artifacts.

### C4 · Founding Partner Uplift Rider — **to be drafted** — 30

Documents the 5% margin uplift for 5 years granted to founding vendors.

### C5 · Print-Partner Sub-DPA (Printful) — 40

Adapt DPA template to Printful's data-processing terms.

### C6 · Print-Partner Sub-DPA (Lulu) — 30

Adapt DPA template to Lulu.

### C7 · Facilitator Curriculum Licence Rider — **to be drafted** — 30

For facilitators licensing outside-created curricula into the platform.

### C8 · AI-Generated Content Policy — **to be drafted** — 25

Human-authorship documentation for any AI-composited works we do

attempt to register.

Section C subtotal: 200 minutes (3 hours 20 minutes)

## Section D — Optional · Internal Compliance Plans (170 min · 2.8 hrs)

These are planning documents, not binding contracts. Ideal for

sign-off by a compliance vendor (Harbor Compliance, Labyrinth, or

Foundation Group), not counsel.

### D1 · Sales-Tax Registration Plan (`16-sales-tax-registration-plan`)

| Sub | Time |
| --- | --- |
| Nexus + monitoring | 20 |
| Product taxability | 10 |
| Marketplace facilitator | 10 |
| Total | 40 |

### D2 · Trademark Filings Plan (`17-trademark-filings-plan`)

| Sub | Time |
| --- | --- |
| Marks + classes | 15 |
| Filing basis + watch service | 10 |
| International + notice | 10 |
| Total | 35 |

### D3 · Copyright Registration Strategy (`18-copyright-registration-strategy`)

| Sub | Time |
| --- | --- |
| Assets + cadence | 15 |
| AI exclusion | 10 |
| Assignments | 10 |
| Total | 35 |

### D4 · State Charitable Solicitation Registration Plan (`21-charitable-solicitation-plan`)

| Sub | Time |
| --- | --- |
| NC + phase 2 states | 20 |
| Required disclosures | 15 |
| Vendor + renewals | 10 |
| Total | 45 |

### D5 · ISTV Contract Analysis Memo (`22-istv-contract-analysis-memo`)

Advisory memo — read only if the ISTV contract is being actively

negotiated. Otherwise archive.

| Section | Time |
| --- | --- |
| Scan for signature | 15 |

Section D subtotal: 170 minutes (2 hours 50 minutes)

## Assumptions & Notes

Times assume the reviewing attorney is a **US generalist with

501(c)(3) experience**. Specialist review (privacy specialist,

IP specialist) would fold in additional time — budget +25% if

splitting across two attorneys.

Times do not include drafting time for the four missing

documents flagged in Section C ("to be drafted"). Budget a

further 3 hours if drafting from scratch is included.

Times do not include meeting time to discuss changes with

the Foundation. Budget 1 hour per section for a wrap

meeting (4 sections × 1 hr = 4 hrs).

Total realistic budget for full ratification including

drafting-gap fills and wrap meetings: ~29 hours of

attorney time.

*First draft — counsel review plan. Comments to legal@birthright.live.*

## EU / UK Compliance Addendum

This document was drafted with EU / UK regulatory alignment in mind. Where

this document conflicts with mandatory rights of an EU or UK resident, the

mandatory local rules prevail. In particular:

GDPR (EU) 2016/679 and UK GDPR apply to processing of personal data

of individuals in the EEA and UK. Where Birthright is the controller,

the lawful bases relied on are: (i) contract necessity, (ii) legitimate

interests (balanced by opt-out), (iii) consent (marketing and non-

essential cookies), and (iv) legal obligation.

ePrivacy Directive (2002/58/EC as amended) applies to cookies and

similar tracking. Non-essential cookies require prior opt-in consent.

EU Consumer Rights Directive (2011/83/EU) — EU/UK consumers have

a 14-day right of withdrawal on distance sales of goods and most

digital services. Where a workshop or digital product has been fully

performed with the consumer's prior consent, the right may be lost.

Digital Services Act (Regulation 2022/2065) applies to online

intermediaries offering services in the EU; Birthright's community

features (posts, DMs, disputes) fall within scope. A single point of

contact is designated at eu-contact@birthright.live.

EU AI Act (Regulation 2024/1689) applies to providers and deployers

of AI systems affecting EU users. Birthright's AI features (Help

Assistant, image generation, image captioning) are labeled as AI-

assisted and are not used for automated decisions with legal effect.

Data transfers out of the EEA/UK/CH rely on the EU Standard

Contractual Clauses (2021/914) and the UK International Data Transfer

Addendum, with a transfer-impact assessment on file for each sub-

processor.

Data Protection Officer (DPO) — Birthright will designate a DPO

once threshold criteria under GDPR Art. 37 are met. Contact:

dpo@birthright.live.

DSAR window — subject access, rectification, erasure, portability,

and objection requests are responded to within 30 days (extendable

by 60 days for complex requests) at privacy@birthright.live.

Supervisory authority — EU/UK residents may lodge a complaint with

their local supervisory authority; a list is available at

https://edpb.europa.eu/about-edpb/about-edpb/members_en (EU) and

https://ico.org.uk (UK).

VAT — Where Birthright's EU B2C digital-service or goods sales

cross applicable thresholds, VAT registration (One-Stop-Shop or

country-by-country) will be completed.